## Sheet1
|  | Authorised By: |  |  | Document Ref:
Issue Number:
Date:
RISK REGISTER
Project Name: | Project x |  |  |  | Project No: |  | Dxxx
Project Address:
Month: | 2012-08-01
Description |  |  | Risk or Opportunity | Likelihood (L/M) | Value to Margin | Mitigation Measure |  | Date Logged | Date Completed | Responsibility
Requirement for additional sensors |  |  | Risk | M | 2000 | Value engineering of design to reduce number of sensors required |  | 2012-05-02 |  | Project Manager
Inverters included in other S/C packages but priced for in AIS tender |  |  | Opportunity | L | 1500 | Try to obtain an interim account agreement at earliest opportunity to flush out any omissions |  | 2012-06-05 | 2012-08-09 | QS
Total Risk (Low)
0
Total Risk (Medium)
2000
Total Opportunity (Low)
1500
Total Opportunity (Medium)
0